# Executive Summary

| Project/Initiative | Lead | Description/Update | Action Required | Key Date(s) |
| --- | --- | --- | --- | --- |
| EPICS Advanced Practices Roll-out | Jessika | AP module 1 will be Building Motivation (prerequisite for all other modules) 145 participants have registered for Module 1 training. | Enrollment open | Enrollment for training: Dec 8 - Jan 16 Module 1 Training: Jan 21 & 29, Feb 2, 11,17 |
| EPICS Dropdown Menu | Justin / Jessika | Approved by ED Table The proposed change to ORCA case notes, requesting EPICS as a subtype, allows for the assessment of frequency beyond formal submission requirements and enhances data accuracy. | Meeting with BTU to discuss next steps for case note in ORCA required | Targeted Implementation by Feb 1, 2026 |
| RS Project | Rav | Meeting with Rob, Rav, Ashley M, took place to review final options doc on Nov 27. Richelle working on Recommendation doc RE: Legal & offence types that would be deemed ineligible for RS. Initial policy draft received from Project Team | Next steps: obtain ED/ADM table feedback on recommendations; begin drafting policy. | Feb 1, 2026 |
| Conditions Project | Rav | 34 Responses received representing 55 offices and 53 court houses Survey Results Summary of survey results shared with Anderw and Lori with APCS Judicial independence noted as a significant barrier to standardized conditions; recommendation to involve Rob Anderson (Court of Justice Legal Counsel) early in discussions. Violation WG - Mtg Notes 2025DEC03.docx | Discuss summary of survey results at next meeting Reach out to Rob Anderson for engagement and next steps | Next Working Group meeting: Jan 21, 2026 |
| ½ Point Policy Changes Stop requiring sex offenders to reach the halfway point of their sentence or order before being eligible for MMU | Justin / Kendra | A change in focus to completely remove Appendix A from policy and all offenders regardless of offense-type would have the same reporting frequency. | Discuss feasibility of removing “Appendix A” at ED/ADM level | Follow up by Feb 1st to plan next steps |
| Overtime Policy | Kendra | Policy draft and supporting documents sent to CCB Managers for feedback Policy and OT request forms developed | Collect feedback from CCB managers and directors | Manager feedback due by Jan 20th Director feedback due on Jan 26th |
| IR Policy Review Review to distinguish natural/sensationalized deaths; streamline reporting with conditional exemptions. | Kendra | Options document submitted for review. ED review complete – option 1 supported “Specify “Major Incident” and Add “Minor Incident” Reporting” | Consult with BTU on IR Bot to ensure alignment Share policy changes with CCB directors for input | Complete both tasks by Feb 1st |
| Violations Working Group (CCB/APS) | Rav | Crown has offered to host training sessions and provide video/podcasts on Crown perspectives for CSO violation packages. CSO material provided to Crown ACPS will provide recommendations for better alignment & clarity on CSO violation packages & training next group meeting. | Finalize training content with Crown | Next meeting January 21 |
| EPICS Evaluation SSII (Wubetu Biabeyin) to lead evaluation. PPDU to provide data/research overview. | Jessika / Divit | Professional Review of EPICS Evaluation received from SSII Initial meeting requested by SSII to confirm details of evaluation plan Evaluation was quoted to require 12-18 months | Schedule meeting with SSI lead – Wubetu Biabeyin With new Lead Coach – once hired | Follow Up with SSII Feb 1, 2026 |

## Executive Summary Queue

| Policy Week Content | PPDU Team | Agenda Items: -General Reminders: QM/WVR, POPA, Lateral Staff Transfer Policy -Toolkit team Recruitment -EPICS Advanced Practice -Privacy Level & AI -IPV Referral Docs | Draft content for internal approval prior to Policy week | Policy week – Jan 26th to Jan 30th |
| --- | --- | --- | --- | --- |
| Policy Toolkit Teams Inactive Toolkits; YOB Alignment, H/F Visits, and Section 19 Review Active Toolkits; Drug Treatment Court drafts pending. | Richelle / Kendra | Toolkit Re-engagement strategy discussed with CCB directors Jan 12th Recruitment will occur for two policy toolkit teams via Microsoft forms during Jan policy week. | Submit formal sign up & Policy week Communications for review by PPDU Manager | Complete by January 21st |
| MMU Ineligibility Case Note Report | Richelle | Stewart Williamson advises other items have come up that take precedent. Anticipated this to be done about February. Ad hoc reports were requested and received to support RS work. | BTU to develop final report in ORCA | Report to be pushed to production by end of Jan 2026 |
| Duress Policy | Kendra | Requested for assistance made by Lindsay S. to draft duress policy with information she has provided. | Complete first draft of policy | Complete draft by January 30th |
| CCB Policy Review | Richelle | Sections 2 has significant HR-related revisions flagged. Section 7 (CQI) & 8 (MMU SOPs only) updates in progress. | Section 7 review by Jessika | In progress |
| RTR - Forms | Richelle | Testing required on Adobe compatibility + training needs before Hub release. Review of all forms on Eforms and CCB Hub complete. | Staff testers required | In progress |
| Essential Service List Update | Rav | Updates to the essential services list are required for finalization and submission to the Deputy Minister before the end of the fiscal year. | Review and update essential services list | Due by March 1st 2026 |
| Drug Offences & Criminal Records – Information Release | Richelle / Kendra | Policy and procedural changes required to align with new legislation/practice around release of information related to drug offences and criminal records. | Identify lead, define scope, and initiate policy review process. | Not yet started; flagged as high priority (Sept 2025) |
| PPDU Change Management & Communications Process - Early Engagement – Involve staff in the drafting of new policies or initiatives through toolkits, focus groups, or project teams. - Director Feedback – Present proposed changes at Decisions and More meetings for Director-level input. - Manager Feedback – Share updates at Leadership Exchange meetings to gather feedback from Managers. - Supervisor/Coach Feedback – Communicate changes at Provincial Coaching Calls to engage Supervisors and Peer Coaches. - Formal Publication – Issue finalized changes through memos and/or highlight them during Policy Week (three times annually). - Staff Engagement – Host Town Halls to inform all CCB staff, ensuring recordings are available on SharePoint for later access. - Deeper Dialogue – Provide virtual open houses for Leadership and staff on key topics to allow time for discussion, reflection, and addressing emerging questions. |  |  |  |  |

# Operational Plan Targets

# CCB Policy Review

- Section 1 – Uploaded to new SharePoint.

- Section 2 – track changes review/approved by Rav; not ready for release.  Old policy uploaded to new SharePoint.

- Section 3 – Uploaded to new SharePoint

- Section 4 – Uploaded to new SharePoint.

- Section 5 – Uploaded to new SharePoint.

- Section 6 – Uploaded to new SharePoint.

- Section 7 – track changes review/approved by Rav; not ready for release.  All policies updated except for 7.03.01 to 7.03.06.

  - Remaining sections to be updated in July 2025; Divit on formatting, Justin leading content update.

- Section 8 - section 8.02 is the only remaining old policy uploaded in all of section 8. **note: 8.02 is MMU SOPs.

  - 8.01 uploaded to policy SharePoint on October 10.

- Section 9 – Uploaded to new SharePoint.

# MMU Sustainment

- MMU Ineligibility case note - Report creation in progress with BTU. Will require final approval. PPDU Projects and Programs

RS Project

- Project Plan first draft complete – Currently undergoing initial review and feedback from Project Team

- Proposal document and process roadmap visual complete

- First draft of policy due on January 12th

- Next Project Team Meeting – Pending following completion of first policy draft

CCB/ACPS Violations Working Group

- ACPS Reps: Lori Dunford, Andrew Shatto

- CCB Reps: Rav Bains (Chair), Justin Kancsal, Richelle Budd, Additional CCB staff as required.

- Next Meeting January 21st

Legislative Policy Changes

Bill S-205 received Royal Assent in October 2024, comes into effect on April 8, 2025. New Peace Bond (fear of domestic violence) has been included in the Criminal Code

- Given the specialized nature of these peace bonds, like the others outlined in the Criminal Code, our current practice would require supervising them on a weekly basis. This has the potential to significantly impact workload depending on the uptake by the Courts.

- To prepare, PPDU will conduct a jscan/HOC targeted request on how other provinces are implementing provisions.

- Interim directive to guide staff on how to supervise these peace bonds though – weekly reporting – has been prepared and is ready for release once approved. Will need decision if appropriate to move forward at this time.

- HOC request completed – pending responses

Non-Legislative Projects

Conditions Project - (Provincial standardized approach to conditions)

- Rav met with Karli Lucas, Director with Edmonton Court Services.  There are 28 unique Court locations which would have different sets of conditions.  Karli will assist in getting the conditions from the locations across the province.  She also indicated that Defence Counsel has reported concerns with having a “cookie cutter” approach to conditions and have deemed it unconstitutional.

- PPDU drafted survey to collect input on difficult to enforce or supervise conditions. Sent out to Managers, Responses due September 19th

  - 19 total responses Received

  - Trends identified in data: Challenging Conditions Survey Update.msg

- Rav has followed up with Karli with respect to progress of getting the conditions –she indicated after speaking with her ED, that next steps would be to get an understanding of what conditions are problematic for Community Corrections (which will be gathered from the survey) and then connect through CCB ED and/or Crown.

- Rav informed Crown’s Adrew Shatto and Lori Dunford of CCB’s survey and will be following up with them once the data is reviewed for next steps.  Both Andrew and Lori indicated an interest in providing assistance. Rav has a scheduled meeting with Andrew and Lori for Dec 3rd for Violations and will discuss next steps for Conditions.  At present, it is considered to approach the matter with ACPS and the judiciary through education.    An analysis through AI did not meeting the desired results.  Focus will be on conditions directly related to the supervision of a client within the job functions of a PO.

eForms Letters

- Plans underway to provide the ‘report letter’ in word format on the CCB Hub so POs can make edits to it to meet client needs.

- EM specific curfew/house arrest permission letter – complaints have arrived that the non-EMP letter is now labelled as “All Other Clients” and this has caused some questions at the frontline. There are other formatting errors showing up on the letter as well.  Draft #3 reviewed – new errors that were not previously there.  Incredibly inefficient process.  Feedback sent August 27.

Overtime Payout Policy

- PPDU to commence a review of current policy and practices related to OT payout.  Rav will connect with COB to review their policies, HR and review the master agreement as first steps.  This will be assigned to Kendra when she commences acting on September 22.

- Kendra has consulted with internal stakeholders and internal OT policy of COB and CMU.

  - Before overtime policy options can be drafted, clear direction is needed on seven foundational parameters, including eligibility, staff classifications, approval process, compensation method, limits, fairness, and budget allocation.

  - These decisions will define the policy’s scope and feasibility and ensure alignment with HR and Finance.

  - Policy draft and supporting documents sent to Managers for input. Input and feedback due by Jan 20th .

# Continuous Quality Improvement (CQI)

- File Review and EPICS Coaching Dashboard – requesting that not only Managers but SPOs have access to this as it will help them determine progress for new staff in the coaching phase. This was presented to Directors at Decisions and More and rec’d support.

- Divit & Jessika to share progress on Casework tracking addition and plans for future access to large scale CQI Dashboard for Supervisors in addition to Managers.

# Policy Toolkits

- YOB/CCRPB Policy alignments to CCB Policy – this team requires repopulating to action the alignment work.

- Violation Guidelines –Consultation with Crown via survey on hold pending combining this work with the ACPS/CCB Working Group, Team has been reviewing policy related to supporting documentation to identify areas where clarification, alignment across order types and updates can be made.

- Home Visit/Field Visit Guidelines – consideration needed if it’s a priority/should continue; if so, this team will need repopulating.

- Drug Treatment Court – ongoing policy analysis. No updates.

- Section 19 – Work was started several years ago to see if the gap left by FASD coordinators could be filled. Their process was prescriptive and appeared time consuming.  Karen Cotton was involved with a Youth FPT table that was looking into best practices for section 19s.  There have been no updates received, and this team has not met in a significant period of time.

GENERAL INISGHTS:

- Toolkit staff have always been stretched thin on these toolkits, which impacts the volume of work that can move forward and the time it takes to do so.  This is increasingly noticeable in the past year.

- Perspective:

  - Most toolkits take 18+ months from start to finish, and that might be a low estimation.  This creates problems – lots of time and effort are invested, priorities change, and all that time is “wasted.”

  - Ideally, to be successful and keep moving forward at a reasonable pace and see toolkits complete, each frontline staff would need to contribute a minimum of 4-5 hours per month that can be dedicated to toolkit work.